## Slide 1: Product Launch Plan: Contoso CloudSuite v4.0
Target launch date: Q3 2025 (September 15, 2025)
Prepared by: Marketing, Product, and Sales teams
Status: In planning
Agenda: Pre-Launch Milestones | Launch Week | Post-Launch Metrics

## Slide 2: Pre-Launch Milestones
April 30: Feature freeze and release candidate to QA
May 31: Beta program launch — 20 design partner customers
June 30: Beta feedback incorporated, GA build signed off
July 31: Sales enablement training completed (all AEs and SEs)
August 15: PR briefings with tier-1 tech media
August 31: Landing page and in-product upgrade messaging live
September 1: Analyst briefings (Gartner, Forrester)
September 10: Embargo lift for press reviews

## Slide 3: Launch Week Plan: September 15-19, 2025
Monday Sept 15: Public announcement — blog post, press release, social media campaign
Monday Sept 15: Email campaign to 45,000 existing customers
Tuesday Sept 16: Live product webinar (target 2,000 registrations)
Wednesday Sept 17: LinkedIn Sponsored Content campaign starts
Thursday Sept 18: Partner enablement webinar for 120 reseller partners
Friday Sept 19: Launch retrospective — war room debrief with all teams
Launch week paid media budget: $120,000

## Slide 4: Post-Launch Success Metrics
30 days: 500 new trial sign-ups from launch campaign
30 days: 15% of existing customers viewed upgrade page
60 days: 50 paid conversions from trial cohort
60 days: NPS survey to beta customers — target score 45+
90 days: $2.1M in new ARR attributed to launch campaign
90 days: 3 tier-1 media reviews published
All metrics tracked in marketing dashboard: go/launch-metrics