# IT Infrastructure Server Migration Plan

Project: On-Premises to Azure Migration | Department: Information Technology

Document Type: Migration Plan | Classification: Internal | Version: 1.2

Owner: Tom Okafor, IT Infrastructure Lead | Date: February 2025

## Executive Summary

Contoso IT Infrastructure will migrate 12 on-premises servers to Microsoft Azure during Q2-Q3 2025. The migration will decommission the Reading data centre, reduce infrastructure operating costs by an estimated 42%, and improve resilience through Azure availability zones. All production workloads will be migrated with a maximum tolerated downtime of 4 hours per server.

## Server Inventory

Total servers in scope: 12

- Application servers: 4 (PROD-APP-01 through PROD-APP-04)

- Database servers: 3 (PROD-SQL-01, PROD-SQL-02, PROD-SQL-RO)

- File/print servers: 2 (PROD-FILE-01, PROD-FILE-02)

- Domain controllers: 2 (PROD-DC-01, PROD-DC-02)

- Monitoring server: 1 (PROD-MON-01)

## Migration Phases

Phase 1 — Assessment (March 2025): Azure Migrate assessment of all 12 servers. Dependency mapping, sizing recommendations, cost modelling. Output: Migration Wave Plan.

Phase 2 — Pilot (April 2025): Migrate 2 non-critical servers (PROD-FILE-02, PROD-MON-01) to validate tooling, networking, and runbook procedures.

Phase 3 — Production Migration Wave 1 (May 2025): Migrate application and file servers (PROD-APP-01 through PROD-APP-04, PROD-FILE-01). Planned maintenance window: Saturday 1am-5am.

Phase 4 — Production Migration Wave 2 (June 2025): Migrate database and domain controller servers. Requires database quiesce and AD replication verification.

Phase 5 — Cutover and Decommission (July 2025): DNS cutover, certificate updates, decommission on-prem hardware, vacate Reading data centre.

## Risks and Rollback Plan

Risk 1: Application compatibility issues post-migration. Mitigation: full regression testing in Azure Dev/Test environment before production cutover.

Risk 2: Network latency increase to branch offices. Mitigation: Azure ExpressRoute circuit to be provisioned before Wave 1.

Rollback Plan: All production servers will be kept powered off (not deleted) for 30 days post-migration. If critical issues arise, revert DNS and re-power on-prem servers within 2 hours.