# Q3 Brand Awareness Campaign Proposal

Document Type: Proposal | Department: Marketing | Sensitivity: Internal

Prepared by: Angela Morales, Head of Brand | Date: January 2025

Budget Request: $450,000 | Campaign Period: Q3 2025 (July-September)

This proposal requests approval for a $450,000 Q3 brand awareness campaign targeting enterprise decision-makers in the financial services and manufacturing verticals. The campaign has three components: digital advertising, an influencer partnership programme, and trade show presence at two major industry events.

## Component 1: Digital Advertising ($220,000)

Channels: LinkedIn Sponsored Content, Google Display Network, and programmatic retargeting.

Target audience: VP and C-suite in companies with 500+ employees in FS and manufacturing.

Key messages: thought leadership, AI-powered automation, enterprise reliability.

KPIs: 4.5M impressions, 18,000 clicks, 900 MQL conversions.

Agency: Fabrikam Creative Agency (existing MSA in place).

## Component 2: Influencer Partnership ($80,000)

Partner with 3 B2B technology influencers with combined LinkedIn following of 280,000.

Content: 2 sponsored posts each, 1 webinar co-host per influencer.

Expected reach: 560,000 impressions at $0.14 CPM.

Authenticity requirement: influencers must be genuine users of the platform (NFR licences provided).

## Component 3: Trade Show Presence ($150,000)

Event 1: Enterprise Technology Summit, Las Vegas, August 12-14. Booth cost: $85,000.

Event 2: Manufacturing Innovation Conference, Chicago, September 9-11. Booth cost: $65,000.

Expected qualified leads from trade shows: 350 combined.

## ROI Projections

Total campaign cost: $450,000

Projected MQLs generated: 1,250

Projected SQLs (20% conversion): 250

Projected closed won deals (15% of SQL): 37 deals

Average deal value: $42,000 (mid-market) = $1.55M projected revenue

3.4x ROI on campaign spend.

## Approval Required

Marketing VP sign-off: required by February 1, 2025

CFO sign-off for amounts over $100K: required by February 5, 2025

Campaign kick-off: March 1, 2025